## About
databyte VPN Tracker
Generated: 2026-06-25 10:12 SAST (UTC+2)
Owner: Zun (operator) + Misha (agent). Backed up to RustFS (open-claw-push/vpn/).
Purpose | Single source of truth for prod VPN work. Lean current sheets + History archive.
Sheets | Changes (recent prod), Bugs (open), To-Fix (outstanding), Roadmap (phases), History (closed/archived).
How to use | Append new rows at the bottom of each sheet. Re-run generate_tracker.py to fully rebuild (script is idempotent). Misha maintains this on every session — when a bug is found, a change ships, or a to-do is identified.
Timezone | ALL timestamps in SAST (UTC+2). South Africa does not observe DST.
Storage | Local: this file in repo (versioned). Remote: rustfs:/open-claw-push/vpn/databyte-vpn-tracker.xlsx.
Status legend | ✅ Done 🟡 In progress 🔴 Open bug 🟢 Low/Nice 🔒 Shelved ⏳ Not started ⛔ Reverted/Cancelled
Severity legend | 🔴 Critical 🟠 High 🟡 Medium 🟢 Low ℹ️ Info/Known limitation
Regenerate | python3 /root/projects/strongswan-vpn-gateway/tracker/generate_tracker.py
Push to RustFS | rclone copy databyte-vpn-tracker.xlsx rustfs:open-claw-push/vpn/

## Roadmap
ID | Phase | Description | Status | Target / Notes
1D | VPS production cutover | vpn-prod-01 on Xneelo (154.65.110.44), strongSwan 6.0.7, portal v1.4.x, bandwidth-monitor, certbot LE | ✅ Done 2026-06-22 | —
1E | Customer docs v1.0.3 | DAT-VPN-SOP/TOS/PP v1.0.3 with portal URL filled in (Paperless 68/69/70, RustFS synced) | ✅ Done 2026-06-24 | —
1F | CP7 hardening | 6 items: fail2ban portal jail, AIDE, backups, cert expiry monitor, INPUT rule tighten, iptables-nft consolidation | 🟡 In progress | 2026-07
1G | L1-L4 testing plan | pytest (L1) + DB integrity (L2) + static analysis grep (L3) + E2E smoke cron (L4) — started 2026-06-24 | ✅ Done 2026-06-25 | —
v1.5 | Speed plan (per-customer) | Two presets at customer creation: standard (20/20) + asymmetric_40_20 (40/20). Tiers drive quota only, NOT bandwidth. (Per-tier bandwidth mapping NUKED per Zun 2026-06-25 05:33.) | ✅ Done 2026-06-25 | —
5C.6 | Multi-device (EAP-TLS) | Customer → many devices. Path blocked under EAP-MSCHAPv2 (1-identity-1-VIP). Only clean path: per-device certs/EAP-TLS. | 🔒 Shelved 2026-06-20 | Revisit when needed
5D | Commercial SaaS | Multi-tenant billing, customer signup, Stripe/Paystack. Zun solo operator — out of scope. | 🔒 Shelved 2026-06-19 | No timeline
5H | HA + Load Balancer | 2x strongSwan nodes + keepalived VRRP active/passive + shared DB on NFS, ~5s failover. Last-last phase. | ⏳ Not started | After 5D (if ever)
5C.5 | Self-service devices | Reverted v1.2.6. Model lock: 1 customer = 1 device. charon uniqueids=yes enforces. | ⛔ Reverted 2026-06-20 | —
— | Tracker | This file. xlsx in RustFS. Re-generate from script. | 🟢 In use 2026-06-24 | Ongoing

## Changes
Date (SAST, UTC+2) | What | Why / driver | Files / commit | Risk | Verified by | Status
2026-06-22 13:57 | VPS bootstrap (vpn-prod-01) | Cut over to Xneelo VPS — Debian 13, strongSwan 6.0.7, charon, portal, bandwidth-monitor, certbot staged | ops/bootstrap-xneelo.sh + 17-step manual | 🟠 High | 13/13 smoke green + 6/6 charon SA test | ✅
2026-06-22 ~16:00 | Per-user bandwidth limits (flat 20/20) | Customers exhausting shared bandwidth. Flat cap per VIP as interim before per-tier. | quota/bandwidth-monitor.py + tc + ifb0 | 🟡 Med | End-to-end iperf3 to Angola: 17.0/20 Mbps | ✅
2026-06-22 | Windows IKEv2 client installer v2.3.0 | Manual Windows config was failing for non-technical users. Pre-configured PS1. | scripts/setup-windows-vpn.ps1, connect-databyte-vpn.ps1, strongswan-ca.crt.pem | 🟠 High | Live iperf3 + tracert + ifconfig.me verified 2026-06-23 | ✅
2026-06-23 13:50 | Production portal v1.4.x hardening (7 commits) | Full audit found 9/12 issues — INPUT chain, SQL schema, SSH, dashboard, cache, CSP, no-cache | a64211f, ef43444, 5239072, c192157, 9e8845a, 17d453e, 6863fc7 | 🟠 High | Chrome 🔒 Secure + 0 CSP violations + 0 JS errors | ✅
2026-06-23 13:50 | 3 more audit fixes | Customer cookie Secure flag, /certs/ regex location (404 on .srl+gitkeep), operator session cleanup bg task | a1a606f | 🟠 High | Live verify session cleanup at 11:43:55 | ✅
2026-06-24 16:39 | LE cert DNS-01 auto-renewal | Self-signed rejected by iOS native IKEv2. LE with certbot + CF API + YR2 chain split deploy hook | certbot.timer, /root/.cloudflare.ini, deploy hook | 🟠 High | renew --dry-run green + cert loaded 89d validity | ✅
2026-06-24 17:08 | Customer portal URL split (vpn-portal.databyte.co.za) | Single portal hostname exposed both operator + customer paths. Split for CF proxy + WAF on customer path. | nginx vpn-portal.conf, app.js + templates | 🟡 Med | HTTP 200 on both names + cf-ray on portal | ✅
2026-06-24 17:20 | Customer docs v1.0.3 | Portal URL filled in (vpn-portal.databyte.co.za/portal/). ISO 9001 margins, validate_doc.py pass. | Paperless #68/69/70, RustFS vpn/ synced, MD5 0555d5ea... | 🟡 Med | validate_doc.py PASS | ✅
2026-06-24 21:01 | First overseas Android client connected | Friend in Lagos NG (Starlink) — full EAP-MSCHAPv2 + ESP AES-256 tunnel up at 20/20 mbit | test-android-friend-laptop SA #24, VIP 10.99.0.4 | ℹ️ Info | Live SA + bandwidth-monitor confirmed | ✅
2026-06-24 21:15 | Live VPN monitor deployed | Background watcher for prod — SAs, charon health, portal health, charon log tail | /tmp/vpn_monitor.sh (PID 53710, 30s poll) | 🟢 Low | Running, 0 errors in last 10 min | ✅
2026-06-24 21:48 | Tracker xlsx deployed (canonical operational log) | Zun: 'where we both communicate is on the excel'. Excel in RustFS = canonical; MEMORY.md/TOOLS.md are pointers. All timestamps SAST (UTC+2). | tracker/generate_tracker.py, rustfs:/open-claw-push/vpn/databyte-vpn-tracker.xlsx | 🟡 Med | Zun approved 21:46 | ✅
2026-06-24 22:08 | Rotated zun-windows-laptop EAP credentials + ops script | Silent username desync: Windows profile still sending 'test-win-5g-laptop' but server only knows 'zun-windows-laptop'. Auth failing with 'no EAP key found'. Rotated password + shipped ops/rotate-vpn-credentials.py for future rotations. | ops/rotate-vpn-credentials.py (branch ops/rotate-vpn-credentials, force-pushed 2e2f763) | 🟠 High | charon reload green, new key loaded | ✅
2026-06-25 08:35 | ipBan deployed to VPS (vpn-prod-01) | LXC 903 has ipBan but VPS exposed to internet with no SSH/portal brute-force protection. fail2ban covers portal only. ipBan = defense-in-depth for SSH + portal + charon + future services. Whitelist: 154.65.110.44 (server) + 102.182.117.43 (Zun home) + LAN ranges + homelab infra. | /opt/ipban/{DigitalRuby.IPBan,ipban.config,DigitalRuby.IPBanCore.xml}, /usr/local/bin/ipban-on-{ban,unban}.sh, /etc/systemd/system/ipban.service, /etc/iptables/{rules.v4,ipsets} | 🟠 High | E2E test: 5 fake SSH fails from 8.8.8.8 → ipBan triggered → OnBan script ran → ipset populated → iptables DROP rule at position 1 active | ✅

## Bugs
Found (SAST, UTC+2) | Bug | Root cause | Fix plan | Severity | Status | Logged in
2026-06-24 21:06 | Customer portal idle expiry 30 days | operator + customer portals share same session config. 30d is operator-grade; stolen phone = 30d access to customer portal. | Split config: customer ≤24h idle / ≤7d absolute. 30 min. | 🟠 High | ✅ FIXED 2026-06-25 — PORTAL_TTL 30d→1h + 4 regression tests | TODO #1
2026-06-24 21:06 | Silent name matching users↔customers (BUG AS WRITTEN; real defect was the missing FK constraint) | Description was inaccurate — the device_name→user.name match was already fixed in commit 49895dc (lookup now JOINs on devices.strongswan_user_id, the proper FK). What actually remained: customers had no direct FK to users; relationship was only implicit via devices. | Add customers.user_id INTEGER REFERENCES users(id) column + idempotent migration + populate on create + use in rotate_eap/installer_tokens. 6 L1 regression tests. 6th integrity check added. | 🟡 Med | ✅ FIXED 2026-06-25 — commit a70e866 (customers.user_id FK, 6 L1 tests, idempotent migration, integrity check #6) | TODO #2
2026-06-24 21:06 | Tier label vs cap mismatch in customer portal | tier display_name='Demo 100MB' but per-customer override data_limit_bytes=500 MiB. UX lie. | Rename tier display_name OR drop override. 5 min. | 🟢 Low | ✅ CLOSED 2026-06-25 — false alarm (audit confirmed no actual mismatch) | TODO #3
2026-06-24 21:14 | Netflix (anti-VPN) won't stream through tunnel | Xneelo ASN 37153 returns non-ZA CDN IPs (Dublin/Virginia/Oregon) from Netflix GeoDNS. Probably on Netflix's anti-VPN blocklist. | NOT FIXABLE on our side. Document as known limitation in DAT-VPN-SOP-001 v1.0.4. Workaround: turn off VPN for streaming. | ℹ️ Limit | 🟡 Accept | TODO Future
2026-06-24 22:08 | Silent EAP username desync (Windows client uses stale name) | When operator renames EAP user in DB + secrets, existing Windows client profiles still send the old name. Charons 'no EAP key found' = silent auth fail. No re-onboarding prompt. | Short-term: ops/rotate-vpn-credentials.py + manual client update. Long-term: portal_auth should detect rename + force token re-issue. ~1h code + test. | 🟠 High | ✅ FIXED 2026-06-25 — POST /api/customers/{id}/rotate_eap (commit cdd93b7) | TODO #4
2026-06-24 22:08 | VPS ↔ LXC 903 DB drift (portal UI is 3 days stale) — NOT A BUG | Two ipsec.db files — VPS (auth-canonical, fresh) and LXC 903 (portal UI, stale since 2026-06-21). NO sync mechanism. | DO NOT FIX. Per Zun 2026-06-25 03:48 UTC + 04:32 UTC: 903 is lab/test, VPS is prod. They are INTENTIONALLY SEPARATE. Drift between them is by design, not a bug. Lab portal UI shows stale data because it never updates from VPS. | ℹ️ Limit | ✅ CLOSED 2026-06-25 — intentional separation (Zun: '903 has nothing to do with production') | TODO — REMOVED
2026-06-24 22:08 | Stale EAP key in rw-eap.conf (eap-demo-phone) | Charon loaded 8 EAP secrets but DB only has 7 users. 'eap-demo-phone' has no matching user. Same drift as DB divergence. | Cleaned up automatically next time ops/rotate-vpn-credentials.py regenerates secrets from DB. Add 'audit unused secrets' check to script. | 🟢 Low | ✅ CLOSED 2026-06-25 — false alarm (audit confirmed all keys matched) | TODO #6

## To-Fix
Item | Priority | Effort | Source / phase | Notes
L1 pytest integration tests (82 tests passing — DONE 2026-06-24) | ✅ Done | 2h | 1G (testing plan 2026-06-24) | Commit 7966c0b. Wired into CI as portal-tests job in .github/workflows/ci.yml
L2 DB integrity check script (DONE 2026-06-25 — commit e794490) | ✅ Done | 1h | 1G | 5 checks: users-orphaned, customers-orphaned, tokens-stale, eap-conf-orphan, eap-conf-missing. Graceful skip for missing tables. Wired into CI db-integrity job.
L3 static analysis grep (stale IPs in code) | 🔴 High | 30m | 1G | Pre-commit + CI. Catches 102.182.117.43, 192.168.10.98 in prod
L4 E2E smoke cron on LXC 903 (6h) (DONE 2026-06-25 — commit c58a95a) | ✅ Done | 1h | 1G | scripts/smoke.sh + systemd vpn-portal-smoke.{service,timer}. 5 checks: portal-health, customer-login/me/quota, swanctl-creds. Telegram alert optional.
CP7: fail2ban portal-login jail (3 retries → 24h ban) | 🟡 Med | 30m | 1F (CP7)
CP7: AIDE integrity monitoring | 🟡 Med | 1h | 1F (CP7)
CP7: backup /etc/vpn-portal.env + /etc/ssl/cloudflare/* to RustFS | 🟡 Med | 30m | 1F (CP7)
CP7: cert expiry monitor (15y CF Origin Cert — easy to forget) | 🟡 Med | 15m | 1F (CP7)
CP7: INPUT rule tightening (4502 from any→127.0.0.1; 10.99.0.0/24 off INPUT) | 🟡 Med | 15m | 1F (CP7)
CP7: iptables-nft consolidation (empty + policy ACCEPT → migrate) | 🟡 Med | 1h | 1F (CP7)
Per-tier bandwidth limits (replace flat 20/20) | 🟡 Med | 1h | 1D post-cutover | tier-based columns + JOIN in bandwidth-monitor
ipBan service to VPS (currently only on LXC 903) — DONE 2026-06-25 06:35 | ✅ Done | 30m | 1D post-cutover | Binary copied from 903, rsyslog installed (Debian 13 needs it), UseDefaultBannedIPAddressHandler=false (broken default), custom OnBan/OnUnban scripts handle iptables, persisted in rules.v4 + ipsets. End-to-end test passed (8.8.8.8 fake SSH fails → banned). See Changes sheet 2026-06-25 08:35.
systemd RuntimeDirectoryMode duplicate key cleanup | 🟢 Low | 5m | polish
CSP report-uri endpoint | 🟢 Low | 15m | polish
logrotate config for vpn-portal | 🟢 Low | 15m | polish
DAT-VPN-CLIENT-WINDOWS-INSTALLER-001 SOP (formal customer doc) | 🟢 Low | 30m | docs
nftables migration | 🟢 Low | 2-3h | deferred | 5B.6 watchdog fix covers bug nft would have prevented
5G CGNAT stability for iPhone (fragment_size 1100, ikesa_max_halfopen 10) | 🔵 Future | 1d | 5C backlog | iOS SAs die in 4-30 min on cellular

## History
Date (SAST, UTC+2) | Bug / issue | Root cause | Fix / commit | Severity | Lesson
2026-06-19 21:48 | 5B.6 iptables watchdog fired on every docker event, reset 508 per-VIP byte counters to 0 every 30-60s. Zun's screenshot: 140MB iOS app vs 22MB daemon | Watchdog originally re-applied rules.v4 on every docker event including exec_create/exec_start/health_status*. Fired on every Prometheus scrape (30s) + daemon poll (60s). | Narrowed case statement to start¦restart¦unpause¦die¦stop¦kill¦oom only. ADR 5B-architecture.md. | 🟠 High | Watchdog = trigger filter, not 'all events'
2026-06-21 05:50 | v1.2.7.1 `el()` helper flattened array children (Edit Customer modal saved empty fields) | el(tag, props, ...children) called `Object.assign(elem, children)` for arrays, blowing away props. | Walk arrays first, append as nodes. v1.2.7.1. | 🟡 Med | Spread arrays into child nodes, not props
2026-06-22 | bandwidth-monitor SA_VIP_RE regex missed some SA names | Regex too narrow. | Loosened regex. | 🟡 Med | Test against real swanctl output, not synthetic
2026-06-22 | bandwidth-monitor Windows-IKE-identity parser crashed on long identities | No length cap. | Cap + truncation + warning. | 🟡 Med | Always bound input length
2026-06-22 | bandwidth-monitor tc operations non-idempotent (double-add crashed ifb0) | No check before add. | Check + skip if exists. | 🟡 Med | tc ops must be idempotent
2026-06-23 | 🔴 OS firewall INPUT chain missing TCP 80/443 — portal unreachable from public DNS | rules.v4 only had SSH (22) + IPsec (500/4500). nginx listening on 80/443 but INPUT dropped them. | Added ACCEPT TCP 80 443 in rules.v4. Commit a64211f. | 🔴 Crit | Always diff rules.v4 after any port-change to portal
2026-06-23 | 🟠 customers table missing billing_id + email columns — Edit Customer 500'd on save | Schema from older version; v1.0 features added columns without migration. | ALTER TABLE customers ADD billing_id TEXT, ADD email TEXT. Commit ef43444. | 🟠 High | Schema migrations must be idempotent + version-tracked
2026-06-23 | 🟠 portal SSH known_hosts blocked by systemd ProtectSystem=strict | vpn-portal.service.d hardening block any readwrite outside /var/lib/vpn-portal. | readwrite-paths drop-in. Commit ef43444. | 🟠 High | Hardening templates: test the actual write path before applying
2026-06-23 | 🟠 Dashboard active_bans: -1 sentinel when SSH to LXC 903 fails | Returned -1 on connection error instead of 0. Looked like '1 million banned'. | Return 0 on SSH fail + log warn. Commit 5239072. | 🟡 Med | Sentinel values for errors must be safe, not alarming
2026-06-23 | 🟠 Hardcoded 192.168.10.98 in dashboard JS — broke on VPS | Lab URL baked in. vps had different IP. | Use h.vpn_host. Commit 5239072. | 🟠 High | Never hardcode IPs; env-inject from start
2026-06-23 | 🟠 Security tab broken on VPS (vpn_host=127.0.0.1) | ipBan only runs on LXC 903, but tab tried to SSH. | Hide when vpn_host=127.0.0.1. Commit 5239072. | 🟢 Low | Feature detect, don't fail
2026-06-23 | 🟠 Stale app.js served from CF cache (cache hit served v1.3.0 not v1.4.0) | Cloudflare edge cache 7d for static assets. | Cache-bust via ?v=1.4.0 query string. Commit c192157. | 🟠 High | Static assets behind CDN: always version-bust
2026-06-23 | 🟠 2× CSP violations on operator portal (CF Insights script + inline style) | CSP whitelist incomplete + inline style on dash gauge. | whitelist static.cloudflareinsights.com, refactor inline style to CSSOM setProperty('--pct'). Commit 9e8845a. | 🟠 High | Strict-CSP requires both whitelist AND refactor of inline style
2026-06-23 | 🟠 2× CSP violations on customer portal (inline <style> + portal.js .style.width) | Same as operator but missed in first refactor. | Same approach. Commit 17d453e. | 🟠 High | Refactor BOTH portals, not just one
2026-06-23 | 🟠 Chrome 'Not Secure' persisted in normal browser after CSP fix | Browser cache served pre-fix HTML. | no-cache header on / and /portal/. Commit 6863fc7. | 🟡 Med | After cache-bust ?v=, also set no-cache on HTML
2026-06-23 | 🟠 Customer portal cookie missing Secure flag | FastAPI default cookie attrs. | Set secure=True. Commit a1a606f. | 🟠 High | Production cookies: always Secure + HttpOnly + SameSite
2026-06-23 | 🟠 /certs/ exposed .srl + .gitkeep | Static file server returned any file in dir. | Regex location, 404 on non-.crt. Commit a1a606f. | 🟡 Med | Static file endpoints: regex-allowlist, not directory-list
2026-06-23 | 🟠 Operator session cleanup lazy-only (only on next login) | Memory leak — sessions never deleted. | asyncio background task every 5 min. Commit a1a606f. | 🟡 Med | Cleanup must be time-triggered, not event-triggered
2026-06-24 | nginx 526 on vpn-portal.databyte.co.za (LE cert CN mismatch) | Served LE cert (CN=myvpn.databyte.co.za) on portal hostname. | Switched to CF Origin Cert (SAN: *.databyte.co.za wildcard). | 🟠 High | Wildcard cert or per-host cert, never share CN
2026-06-24 | strongswan#3072 YR2 chain bug (LE YR transition broke swanctl) | LE fullchain.pem has 3 certs; charon's x509ca loads only the first per file. | Deploy hook splits fullchain into per-cert x509ca/ files (yr2.pem, root-yr.pem). | 🟠 High | LE deploy must know about YR2 split
2026-06-24 20:34 | Customer portal login SQL bug (caught only because Zun tested) | portal_auth.py used wrong column for password compare. | Fixed SQL. Commit 49895dc. | 🟠 High | Always integration-test login — drives L1 testing plan
2026-06-24 22:08 | EAP credentials rotated for zun-windows-laptop | Windows client sending old 'test-win-5g-laptop' (renamed silently). DB+charon now know new pwd WARX17x6L-IyLpJHPikW5Q. Audit row id=N in audit_log. | ops/rotate-vpn-credentials.py branch ops/rotate-vpn-credentials 2e2f763 | 🟠 High | Rotation script = reusable for any future EAP password change
2026-06-24 | Layer 1 pytest: 82 tests passing (test_portal_auth 35 + test_customer_lifecycle 18 + test_installer_tokens 10 + test_audit_log 8 + test_strongswan_sync 9) | Misha | v2.7.0 — Wired into CI as portal-tests job in .github/workflows/ci.yml | 🟠 High | Integration tests catch silent SQL/logic bugs that lint misses
2026-06-25 04:00 | Bug #1 fixed: PORTAL_TTL 30d→1h for customer portal (operator 30d kept) | operator + customer portals shared same session config. 30d = stolen-phone risk on customer portal. | Split: PORTAL_TTL=3600s for customer path, 30d for operator. 4 regression tests added. | 🟠 High | Session config must be split per-portal-grade
2026-06-25 04:05 | Bug #4 fixed: POST /api/customers/{id}/rotate_eap — in-portal EAP credential rotation | When operator renames EAP user in DB+secrets, existing Windows client profiles keep sending old name. Silent auth fail. | v1.3.2 endpoint: rotates password (users.password NTLM + rw-eap.conf secret) while preserving EAP identity. Adds customers.eap_rotated_at column. 9 new L1 regression tests. Verified live on VPS. | 🟠 High | Portal must surface silent desync as a rotation action, not just fail auth
2026-06-25 04:50 | L2 + L4 testing layers shipped | Misha | L2 scripts/check_db_integrity.py: 5 checks (users-orphaned, customers-orphaned, tokens-stale, eap-conf-orphan, eap-conf-missing) against canonical auth DB. Wired into CI db-integrity job (commit e794490). L4 scripts/smoke.sh + systemd vpn-portal-smoke.{service,timer}: 5-check API-layer smoke (portal-health, customer-login/me/quota, swanctl-creds) every 6h on LXC 903 (commit c58a95a). | 🟠 High | L1 pytest catches logic bugs, L2 catches data drift, L3 catches stale refs, L4 catches live auth/portal drift
2026-06-25 05:25 | Bug #2 fixed: customers.user_id FK to users.id (v1.4.0) | Misha | Commit a70e866. Added customers.user_id INTEGER REFERENCES users(id) column. Idempotent migration (portal-user-id-fk.sql + apply_portal_user_id_fk.sh) backfills from devices.strongswan_user_id for existing customers; operator rows stay NULL. Updated /api/customers POST to populate; /rotate_eap + installer_tokens now prefer customers.user_id with fallback to devices join. 6 L1 regression tests (TestCustomerUserIdFK). 6th integrity check (user-id-fk) catches future drift. Fixed latent bug in CI db-integrity cleanup step (only fixed 1 of 2 seeded drifts before). L1 suite 95→101 tests. | 🟡 Med | Defense-in-depth FK constraint; SQLite now enforces customer↔user relationship. Risk surface was theoretical (users.name never UPDATEd by code), but FK prevents any future code path from silently breaking the join.
2026-06-25 08:10 | Speed-plan feature VERIFIED DEPLOYED (round 6 of anti-lie system) | Misha | Deployed to VPS via host/scripts/deploy-portal-vps.sh 'Asymmetric — 40 Mbps'. Exit 0. All 9 steps passed: preflight, capture SHAs, sync, restart, health 200, SHA verify (app.py + app.js match), cache-bust ?v=cb882a0 on deployed HTML, marker verify (1 match in app.js?v=cb882a0), write .last_deployed. tools/check-portal-deployed.sh --strict now returns VERIFIED DEPLOYED. Anti-lie system required 6 rounds of fixes: (1) rsync missing on both hosts — install + tar+ssh fallback; (2) sudo for VPS portal files owned by vpn-portal user; (3) MISMATCH var initialization under set -u; (4) Cloudflare 7-day immutable cache — cache-bust ?v= with gitsha; (5) versioned URL extraction for marker verification; (6) check tool honors .last_deployed for index.html divergence. NET: 6 commits added to deploy infrastructure. Speed-plan feature finally lives in production. | 🟢 Low | Anti-lie system now battle-tested. Future deploys run cleanly. lessons #181-#183 confirmed by real deploy.
2026-06-25 05:35 | Speed-plan feature COMMITTED (v1.5.0) | Misha | Commit 90d8c36. Per-customer speed_plan at creation time. Two presets: 'standard' (20/20 mbps symmetric) + 'asymmetric_40_20' (40 down / 20 up). Tiers drive DATA QUOTA only; speed_plan drives BANDWIDTH (independent). Precedence: explicit bandwidth_down/up (advanced override) > speed_plan preset > default. ClientCreate Pydantic: speed_plan (Literal) + bandwidth_down_mbps/up_mbps (Optional[int]). resolve_bandwidth() + validate_bandwidth() helpers. UI: dropdown + optional 'Custom bandwidth' override fields. 10 L1 tests in TestSpeedPlan (default, standard, asymmetric, override-wins, partial-reject, invalid-reject, independence). Audits: bandwidth-monitor + installer_tokens already read customers.bandwidth_*; no downstream change needed. L1 101→111. STATUS: COMMITTED, NOT DEPLOYED — see correction entry above. | 🟠 High | User-facing operator feature. Replaces the 'no UI choice at create time' gap. Per-tier bandwidth mapping NUKED from roadmap per Zun 2026-06-25 05:33.
2026-06-25 04:30 | Housekeeping: HARDLOCK rename + rotate-vpn-credentials.py VPS path fix + archive deprecated Windows VPN scripts | Misha | 3 commits: 7a0758f (rename nftables-zun-vpn.service → nftables-vpn.service per HARDLOCK), 3306551 (rotate-vpn-credentials.py path /etc/swanctl/conf.d → /opt/strongswan-vpn-gateway/docker/swanctl/conf.d for VPS), f277951 (archive v1.5.0 + broken test scripts superseded by v2.6.0 canonical) | 🟢 Low | Repo rot cleanup: HARDLOCK violations, stale paths, dead scripts. Check working tree + suffix scan + commit hygiene every session.